## Project Parthenon Timeline
Project Parthenon - Development Timeline (v1.1, re-baselined 2026-04-27)
Basis: 25 hrs/week (~65% dedication) ¦ Solo developer + AI assistance ¦ External workbook deps: out of scope
# | Work Item | Work Involved | Timeline (Weeks)
BUCKET 0: PHASE 1 PREREQUISITES (gating deferred investigations - v1.1)
P1 | Per-asset parameter inventory | Horizontal scan of Project Info x 120 slots. Confirms 590+ parameter claim and produces the parameter list for schema design. | 0.3
P2 | 78-asset list by country/tech | Enumerate the 78 active assets in F1 with country (DE/UK/NL) and technology (Solar / BESS / Solar+BESS). Feeds asset registry. | 0.05
P3 | Time Inputs (M) disagg mechanic (partial) | Decode annual->monthly disaggregation pattern (just the mechanic). Full deep-dive of 603k formulas can defer until before Revenue (#4). | 0.5
P4 | 75 PLW edge-case rows - per-row inspection | Catalogue what makes each row's formula differ across time cols. Informs translator override-map design (#1). | 0.4
P5 | 184 changed PLW rows - F3 vs F1 formula comparison | Side-by-side diff to understand what ASE actively edits each quarter. Informs translator and re-validation strategy. | 0.2
Bucket 0 Subtotal (must complete before Phase 1 / translator) |  |  | 1.45
BUCKET 1: CORE ENGINE (Replicating the Excel calculation logic in Python)
1 | Formula Extraction & Translation Framework | Parse 915 PLW formula rows (cols AB-QF) from .xlsm. Excel-to-Python translator covering 26 functions. Per-column override map for 75 edge-case rows whose formulas differ across the 421 time cols. Re-runnable each quarter with formula-delta report. | 2.5
2 | Flags & Timing Block | ~100 formula rows: construction dates, COD flags, monthly/quarterly period flags, inflation index lookups from Time Inputs (A) (64,413 PLW refs). | 0.8
3 | Production Engine | ~20 formula rows: Solar yield (P50/P90 selection), degradation curves, curtailment, availability, BESS dispatch & repower logic. Smallest calc block. | 0.6
4 | Revenue Engine (LARGEST BLOCK) | ~200 formula rows: PPA, CfD, FiT/FiP, merchant pricing, GoO, tolling, floor revenue. Country-specific logic DE/UK/NL. XLOOKUP into Time Inputs (A) for pricing curves; depends on Time Inputs (M) annual->monthly disagg. | 2.8
5 | OpEx Block | ~60 formula rows: O&M Solar/BESS, insurance, land lease, asset management fees, revenue-dependent lease, community benefit. | 1
6 | Depreciation & Fixed Assets | ~70 formula rows: 7 depreciation categories with fully-depreciated checks, BESS repower depreciation, Fixed Assets closing balance. | 1
7 | VAT | ~50 formula rows: VAT on CapEx/OpEx/Revenue, receivable/payable tracking, VAT facility drawdown/repayment. | 0.6
8 | Senior Debt & DSCR Solver | ~100 formula rows: debt drawdown, repayment, cash sweep, interest calc, DSCR sculpting. Fixed-point solver with TWO criteria (debt_delta<0.2 AND Use_delta<0.2) plus max_iter cap (VBA has none). Includes DSRA + CapEx repower account; depends on HoldCo_Facility decode. | 1.6
9 | Tax | ~80 formula rows: corporate tax, loss carry-forward, local tax basis, interest deduction limitation. Country-specific rates for DE/UK. | 1.2
10 | SHL & Distribution Waterfall | ~110 formula rows: shareholder loan drawdown/repayment/IDC, distribution calcs, lock-up DSCR test, dividends, equity issuance/buyback, withholding tax. | 1.4
11 | IRR & Financial Statements | ~140 formula rows: XIRR (project & equity level), quarterly consolidation via SUMIFS, income statement, balance sheet, cashflow statement. Depends on HoldCo CFs (664k formulas) + HoldCo income decode. | 1
12 | Scenario Engine | Replicate Sensis mechanism: 24 scenario slots, 15+ levers across 4 sections (Operations / Production / Uncontracted revs / Contracted revs). Mixed types (boolean/enum/percentage). Lever_type discriminator in schema. VBA flag-comparison subtlety (string 'True' vs boolean True) replicated exactly. | 1.2
13 | Sensitivity Analysis | Single-variable & multi-variable sweeps, tornado chart data generation. Vectorized across all 78 assets - replaces 1,872 sequential Excel recalcs with one pass. | 0.8
14 | Validation & Debugging | Cross-check Python output vs Excel for all 78 assets x 170 metrics x 421 periods. Oracle confirmed available (PLW + Quarterly Output cached). Explicit per-row tests for all 75 edge-case rows + country-specific branches. | 1.6
Bucket 1 Subtotal (915 PLW formula rows, 75 edge cases, 26 Excel functions) |  |  | 18.1
BUCKET 2: DATA & INFRASTRUCTURE (Making it a working application)
15 | Database Schema & Migrations | PostgreSQL tables: assets, parameters, time series, metrics, scenarios (with lever_type discriminator), versions. Alembic migrations. Table partitioning for 3M+ cells. | 1
16 | Excel Ingestion Pipeline | Parse .xlsm into normalized DB tables. 7 input sheets (228K cells, 25K input levers). Read hidden rows (Time Inputs A 69%, HoldCo income 80%). Filter ~490 add-in named-range noise (Capital IQ/Bloomberg/Smartview/Access). Log #REF! errors (40 in F2). Snapshot external SharePoint workbook values inline (Project Canopy, CIP v7) - external files OUT OF SCOPE. | 1.7
17 | Quarterly File Comparison Engine | Structural fingerprint diff with row-shift alignment (not equality - 13 named ranges shifted +2 rows F3->F1). Parameter-level change detection. PLW formula-row delta report (184 rows changed F3->F1). Automated change report. | 1
18 | FastAPI Backend | REST API: CRUD endpoints, scenario management API, quarterly diff API, report generation trigger, calc engine invocation. | 1.2
19 | GTC Reporting (21 sheets) | Asset workings (1.19M cells) is a reshape collapsing to one groupby/pivot, not 21 bespoke implementations. PnL/BS projections are generic ROUND(SUMIF(...)) aggregators. Single aggregator + template registry. | 1
20 | Excel Report Export | Generate formatted .xlsx matching audit requirements. Reproduce GTC sheet layouts using openpyxl/xlsxwriter. | 0.6
Bucket 2 Subtotal |  |  | 6.5
BUCKET 3: APPLICATION LAYER (Login, UI, deployment)
21 | Authentication & Security | Streamlit built-in auth, basic session handling. Lean for prototype. | 0.3
22 | Dashboard & UI | Asset browser, portfolio view, scenario comparison screens, charts, filters. Functional over beautiful for prototype. | 1.2
23 | Error Handling & Logging | Input validation, calc engine error trapping, audit logging. | 0.3
24 | Deployment | Docker setup, environment config, basic CI/CD pipeline. | 0.3
25 | Documentation & Handover | User guide, API documentation, architecture docs for future developers. | 0.3
Bucket 3 Subtotal |  |  | 2.5
BUCKET 0B: GATED DEEP-DIVES (run concurrently with Bucket 1, before specific blocks)
G1 | Time Inputs (M) full deep-dive | Complete the 603k-formula monthly disagg analysis. Required before Revenue (#4). | 0.4
G2 | HoldCo_Facility decode | 92k formulas, facility-level debt model. Required before Senior Debt (#8). | 0.3
G3 | HoldCo CFs & Valuation decode | 664k formulas, 3,379 rows. Second-largest formula sheet. Required before IRR (#11). | 0.7
G4 | HoldCo income decode | 155k formulas, 80% rows hidden. Confirm what's alive vs legacy. Required before IRR (#11). | 0.2
Bucket 0B Subtotal (gated deep-dives, concurrent with Bucket 1) |  |  | 1.6
BUFFER
| Debugging Surprises & SME Response Delays | Edge cases in country-specific logic (DE/UK), Finance team validation turnaround, unexpected formula behaviour, integration issues. Reduced from v1.0 (2.2w) - net effort moved into bucket subtotals where measurable. | 1.4
GRAND TOTAL |  |  | ~30 weeks
ESTIMATED DURATION (Bucket 0B concurrent with Bucket 1) |  |  | ~7.5 Months
NOTES & ASSUMPTIONS
v1.1 NOTES (re-baselined 2026-04-27 against 23-Apr deep re-analysis):
1. PLW has 915 rows with time-axis formulas (was 877 in v1.0) over cols AB-QF (not M-PQ). 26 Excel functions confirmed.
2. 75 PLW edge-case rows have formulas that differ across time cols (was 13 in v1.0) - per-column override map required in translator.
3. PLW is a single-asset-at-a-time model (421 time columns). Python engine vectorizes across all 78 assets simultaneously.
4. DSCR solver: TWO convergence criteria (debt_delta<0.2 AND Use_delta<0.2). VBA has no max-iter cap; Python adds one with hard error.
5. Asset workings (1.19M cells) is a reshape, not 21 bespoke implementations - collapses to one groupby/pivot. GTC reporting reduced 1.4w -> 1.0w.
6. Revenue engine is the single largest risk item: 200 formula rows with country-specific branching (DE/UK/NL).
7. Sensis: 15+ levers across 4 sections (Operations / Production / Uncontracted revs / Contracted revs), mixed types (boolean/enum/percentage). Schema needs lever_type discriminator.
8. PLW formulas not frozen between quarters: 184 rows changed F3->F1 (11.5%). Translator re-runnable each quarter with formula-delta report.
9. Project Info shifts row indices between quarters (+2 rows F3->F1). Structural fingerprint comparator must align by section label / named-range identity, not equality.
10. External SharePoint workbooks (Project Canopy v14/v24/v30, CIP v7 Capacity) are OUT OF SCOPE - ingestion snapshots cached values inline only.
11. Validation oracle confirmed available (probed 2026-04-27): F1 PLW deep-region 64% cached, Quarterly Output 62%. No manual F9-and-save needed.
12. Bucket 0 (1.45w) is NEW v1.1 work - prerequisites that gate Phase 1 schema/ingestion. Bucket 0B (1.6w) deep-dives run concurrently with Bucket 1.
13. Buffer reduced 2.2w -> 1.4w; net effort moved into measurable bucket items (translator +0.5, debt +0.2, scenario +0.2, ingestion +0.3, GTC -0.4).
14. Assumes Finance team SME availability for validation queries within 2-3 business days.