PROJECT PARTHENON

6-Month Development Timeline

Production-Ready Prototype

Financial Modeling Platform for Scenario & Sensitivity Analysis

| Prepared for: | Ampyr Energy Tech Solutions |
| --- | --- |
| Prepared by: | Ankit Agarwal, GM Product & Tech |
| Date: | March 2026 |
| Duration: | 6 Months (April - September 2026) |
| Classification: | Internal / Confidential |

# Executive Summary

Project Parthenon replaces a 2-3 hour Excel-based scenario analysis workflow with a Python-powered web application. The platform ingests the quarterly ASE financial model, replicates the full calculation engine in Python, and enables real-time scenario and sensitivity analysis across the entire 78-asset renewable energy portfolio.

| Metric | Current State | Target (Month 6) | Improvement |
| --- | --- | --- | --- |
| Scenario Run Time | 2-3 hours | < 30 seconds | 360x faster |
| Quarterly Update | 2-3 days manual | < 4 hours | 90% reduction |
| Concurrent Scenarios | 1 at a time | Unlimited parallel | N/A |
| Asset Coverage | 78 assets (all recalc) | 78 assets (selective) | Only changed assets recalculate |

## Scope & Assumptions

- Solo developer (GM Product & Tech) with AI-assisted development, ~20 hrs/week dedicated

- Tech stack: Python FastAPI + PostgreSQL + Streamlit

- Full calculation engine replication (all 1,609 rows of Project Level Workings)

- All 6 scenario levers: Devex, Capex, Opex, Production, Revenue, Financing

- All 21 GTC reporting sheets included

- Quarterly file comparison and update workflow

- Total estimated effort: ~480 development hours across 24 weeks

# Visual Timeline Overview

The 6-month plan is organized into 3 phases with overlapping workstreams:

| Workstream | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Phase 1: Foundation |  | Phase 2: Calc Engine |  | Phase 3: Scenario + Polish |  |
| Database & Ingestion |  |  |  |  |  |  |
| Quarterly Diff Engine |  |  |  |  |  |  |
| Streamlit UI Shell |  |  |  |  |  |  |
| Calc: Production & Revenue |  |  |  |  |  |  |
| Calc: OpEx / Tax / Depr |  |  |  |  |  |  |
| Calc: Debt & DSCR Solver |  |  |  |  |  |  |
| Calc: IRR & Waterfall |  |  |  |  |  |  |
| Scenario Engine (6 levers) |  |  |  |  |  |  |
| GTC Reporting Sheets (21) |  |  |  |  |  |  |
| Validation & UAT |  |  |  |  |  |  |

M1 = Month 1 (April 2026), M6 = Month 6 (September 2026)

# Month-by-Month Breakdown

Month 1: Foundation & Data Layer

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W1-W2 | Database Design | PostgreSQL schema: assets, parameters, time_series, quarterly_metrics, model_versions, scenarios | Schema review |
| W2-W3 | Excel Ingestion | Ingest .xlsm/.xlsb into DB: Project Info, Country Inputs, Financing Inputs, Time Inputs (A/M/Q) | 78 assets loaded |
| W3-W4 | Streamlit Shell | Asset browser, metric explorer, file upload UI, basic authentication | Demo to Finance |

Key milestone: Upload the ASE Excel file and browse all 78 assets with their parameters in the web UI.

Month 2: Quarterly Output Ingestion & Diff Engine

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W5-W6 | Output Ingestion | Parse Quarterly Output (36K rows x 433 cols), normalize 170 metrics per asset into quarterly_metrics table | 3.1M cells loaded |
| W6-W7 | Structural Fingerprint | Automated structural comparison engine using STRUCTURAL_MAP baseline. Detect row insertions, parameter changes, new assets | Diff report generated |
| W7-W8 | Version Management | Quarter-over-quarter comparison dashboard, change heatmaps, approval workflow for new baseline | Compare 2 quarters |

Key milestone: Upload a new quarterly file, see exactly what changed vs. the previous quarter, approve as new baseline.

Month 3: Calc Engine - Production & Revenue

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W9-W10 | Formula Extraction | Extract all formulas from Project Level Workings .xlsm, map dependency graph, identify calculation blocks | Block map complete |
| W10-W11 | Flags & Production | Python modules: project flags/timings, construction schedule, net production (P50/P90), degradation, curtailment | <0.01% vs Excel |
| W11-W12 | Revenue Engine | PPA revenue, merchant revenue, RoC/CfD, FiT/FiP, indexation logic, country-specific contract types (348 formula rows) | <0.01% vs Excel |

Key milestone: Python-calculated Production and Revenue match Excel output within 0.01% for all 78 assets.

Risk flag: Revenue engine is the most complex block (348 rows of country-specific logic). May extend into Month 4.

Month 4: Calc Engine - Costs, Tax & Debt

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W13-W14 | OpEx & EBITDA | Operating expenditure module, land lease, insurance, O&M, management fees, EBITDA calculation | <0.01% vs Excel |
| W14-W15 | Capex & Tax | Devex/Capex schedule, depreciation (country-specific), corporate tax, VAT, working capital | <0.01% vs Excel |
| W15-W16 | Debt & DSCR | Senior debt drawdown/repayment, DSCR sculpting with Newton-Raphson iterative solver, reserve accounts | Circular ref solved |

Key milestone: Complete financial cascade from Production through to Debt service for all assets.

Risk flag: DSCR circular reference solver is technically the hardest component. Fallback: use fixed-point iteration if Newton-Raphson convergence is problematic.

Month 5: Scenario Engine & Validation

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W17-W18 | IRR & Distribution | Distribution waterfall, equity returns, XIRR calculation, HoldCo aggregation, financial statements assembly | Full cascade validated |
| W18-W19 | Scenario Framework | 6 scenario levers (Devex/Capex/Opex/Production/Revenue/Financing), parameter override system, selective recalculation via dependency graph | Scenario runs <30s |
| W19-W20 | Sensitivity Analysis | Single-variable sensitivity tables, multi-variable tornado charts, scenario comparison side-by-side, parallel scenario execution | Demo to Finance |

Key milestone: Run a complete scenario changing 3 asset production assumptions and see updated IRR/DSCR/NPV in under 30 seconds.

Month 6: GTC Reporting, Polish & Launch

| Week | Focus Area | Key Deliverables | Status Gate |
| --- | --- | --- | --- |
| W21-W22 | GTC Reporting Sheets | All 21 GTC sheets: PnL/BS projections, CF Capital Strategy, Valuation, OpCo Performance, Dev Pipeline, QREP, GTC Summary | Reports match Excel |
| W22-W23 | Export & Integration | Excel report generation (audit-compliant), scenario comparison exports, PDF summary reports | Export validated |
| W23-W24 | Production Readiness | Error handling, logging, deployment config, user documentation, UAT with Finance team, bug fixes | Finance sign-off |

Key milestone: Finance team runs a full quarterly update + scenario analysis cycle end-to-end without touching Excel.

# Deliverables Summary by Month

| Month | Core Deliverable | Demo-able Feature | Cumulative % |
| --- | --- | --- | --- |
| Month 1 | Database + Ingestion + UI Shell | Browse 78 assets in web UI | 15% |
| Month 2 | Quarterly Output + Diff Engine | Upload new file, see changes | 30% |
| Month 3 | Calc: Production + Revenue | Python matches Excel for P&R | 50% |
| Month 4 | Calc: Costs + Tax + Debt/DSCR | Full financial cascade works | 70% |
| Month 5 | Scenario Engine + Sensitivity | Run scenarios in <30 seconds | 85% |
| Month 6 | GTC Reports + Production Launch | Full quarterly cycle without Excel | 100% |

# Risk Register

The following risks have been identified with the aggressive 6-month timeline. Each includes a mitigation strategy.

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Revenue engine complexity exceeds estimate (348 rows, country-specific logic) | HIGH | Medium | Start revenue block first in Month 3. If delayed, defer 2-3 edge-case contract types to post-launch update. |
| DSCR circular reference solver convergence issues | HIGH | Low-Med | Implement both Newton-Raphson and fixed-point iteration. Use Excel COM (xlwings) as validation oracle during development. |
| Part-time bandwidth insufficient for full calc engine | HIGH | Medium | Months 3-4 are the critical path. If behind schedule by Week 14, recommend adding a contract Python developer for calc engine blocks. |
| Numerical divergence between Python and Excel (>0.01%) | Medium | Medium | Block-by-block validation against Excel at each stage. Accept <0.1% divergence for edge cases. Log all divergences for review. |
| Quarterly file structure changes break ingestion pipeline | Medium | Low | STRUCTURAL_MAP baseline with automated drift detection. Alert on any structural change before processing. |
| Streamlit performance with large datasets (3.1M cells) | Low | Medium | Pre-aggregate data at ingestion time. Use server-side pagination. Cache frequently accessed queries in Redis if needed. |

# Critical Path & Decision Points

The following checkpoints require management decisions:

## End of Month 2 - Go/No-Go for Calc Engine

- Foundation platform is working: data ingestion, quarterly comparison, basic UI

- Decision: Proceed with in-house calc engine build vs. exploring Excel-as-a-Service alternative

- If calc engine build is approved, Months 3-4 become the critical path

## End of Month 4 - Resource Assessment

- Full financial cascade (Production through Debt) should be complete

- If behind schedule: recommend hiring a contract Python developer for remaining blocks

- If on track: continue solo for scenario engine and GTC reporting

## End of Month 5 - UAT Readiness

- Scenario engine functional: Finance team begins parallel testing (Excel vs. App)

- Decision: Launch timeline - immediate rollout vs. extended parallel-run period

- GTC reporting sheets may shift to Month 7 if core scenarios take priority

# Technology Stack

| Component | Technology | Rationale |
| --- | --- | --- |
| Backend API | Python FastAPI | Async, high performance, auto-docs, type safety |
| Database | PostgreSQL | JSONB for flexible params, table partitioning for 3.1M+ cells |
| Calc Engine | Python + NumPy | Vectorized computation, selective recalc via dependency graph |
| Frontend | Streamlit | Rapid prototyping, Python-native, low frontend overhead |
| Excel Parsing | openpyxl + pyxlsb | Formula extraction (.xlsm) + cached values (.xlsb) |
| Deployment | Docker + internal hosting | Containerized for consistency, internal deployment |

# Resource Requirements

| Resource | Commitment | Period | Status |
| --- | --- | --- | --- |
| GM Product & Tech | 20 hrs/week dedicated | Months 1-6 (full duration) | Confirmed |
| AI Development Assistant | Claude Code (AI pair programming) | Months 1-6 (full duration) | Confirmed |
| Finance Team (SME) | 4-6 hrs/week for validation | Months 3-6 (calc validation) | To be confirmed |
| Contract Python Dev (contingency) | Full-time if triggered | Month 5-6 (if behind schedule) | Contingency only |
| Infrastructure | PostgreSQL server + app hosting | Month 1 onwards | To be provisioned |

# Success Criteria

The prototype will be considered successful when:

| # | Criterion | Measurement |
| --- | --- | --- |
| 1 | Scenario analysis completes in <30 seconds for any single lever change | Timed test: change Production for 3 assets |
| 2 | Python calc engine matches Excel output within 0.01% for all 170 metrics | Automated validation suite across all 78 assets |
| 3 | Quarterly file upload + comparison completes in <4 hours (vs. 2-3 days manual) | End-to-end quarterly update cycle |
| 4 | All 6 scenario levers functional: Devex, Capex, Opex, Production, Revenue, Financing | Finance team runs each lever successfully |
| 5 | 21 GTC reporting sheets generated from app match Excel baseline | Side-by-side comparison report |
| 6 | Finance team can run parallel analysis (Excel vs App) for one full quarter | No blockers during parallel run |
| 7 | Selective recalculation: changing 3 assets does not recalculate remaining 75 | Performance log shows targeted recalc |
| 8 | Quarterly structural drift detection catches >95% of file changes automatically | Test with known-changed quarterly files |

# Immediate Next Steps

Upon approval of this timeline:

- Provision PostgreSQL database and application hosting environment

- Confirm Finance team availability for validation support (Months 3-6)

- Begin Month 1: Database schema design and Excel ingestion pipeline

- Schedule bi-weekly progress demos with stakeholders