PROJECT PARTHENON

Development Plan

Financial Modeling Platform

Month-by-Month Implementation Roadmap

| Prepared for: | Ampyr Energy Tech Solutions |
| --- | --- |
| Prepared by: | GTC Product & Technology |
| Date: | March 2026 |
| Version: | 1.0 |
| Classification: | Internal / Confidential |

# Executive Summary

Project Parthenon transforms Ampyr GTC’s financial modeling workflow from a 2–3 hour Excel-based process into a real-time web application. The platform ingests the core ASE financial model (120 asset slots, 170 metrics, 35-year horizon), enables instant scenario and sensitivity analysis, and automates quarterly model updates.

| Assets | Current Runtime | Target Runtime | Timeline |
| --- | --- | --- | --- |
| 78 real + 42 placeholder | 2–3 hours / scenario | < 5 seconds / scenario | 12 months (6 phases) |

Tech Stack: Python FastAPI + PostgreSQL + Streamlit

Approach: Hybrid (Option C) — Ingest Excel output values immediately for reporting; build Python calculation engine incrementally, validated against Excel at every step.

# Timeline Overview

The project is divided into 6 phases, each delivering independent value. The first usable product ships at the end of Month 2.

| # | Phase | Duration | Months | Key Outcome |
| --- | --- | --- | --- | --- |
| 1 | Foundation | 8 weeks | M1–M2 | Read-only platform |
| 2 | Reporting Engine | 6 weeks | M3–M4 | Auto-generated reports |
| 3 | Calc Engine: Core | 12 weeks | M4–M7 | P&L recalculation |
| 4 | Calc Engine: Finance | 8 weeks | M7–M9 | Full model parity |
| 5 | Scenario Engine | 6 weeks | M9–M10 | Real-time scenarios |
| 6 | Satellite Frontends | 8 weeks | M11–M12 | Multi-team platform |

# Phase 1: Foundation

|  | PHASE 1: Read-Only Platform | M1–M2 |
| --- | --- | --- |

Goal: Ingest the core Excel model into PostgreSQL and build a browsable, queryable platform with quarterly diff capabilities. This phase delivers the first usable product.

## Month 1: Database & Ingestion

Stand up the project infrastructure, define the database schema, and build the Excel ingestion pipeline.

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W1–W2 | Project setup: FastAPI skeleton, PostgreSQL, Alembic migrations, Docker Compose | docker-compose.yml, alembic/, app/models/ | Dev env ready |
| W2–W3 | Database schema: assets, asset_parameters, time_series_inputs, country_parameters, financing_terms, model_versions | app/models/*.py, migrations/ | Schema deployed |
| W3–W4 | Excel ingestion pipeline: pyxlsb/openpyxl reader for all 6 input sheets + Quarterly Output | app/ingestion/xlsb_reader.py, normalizer.py | Full ingestion |
| W4 | Version management: upload tracking, file hashing (SHA-256), baseline locking | app/api/versions.py | Version system live |

## Month 2: Diff Engine & Dashboard

Build the quarterly comparison engine and the first Streamlit UI for browsing assets and viewing changes.

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W5–W6 | Diff engine: structural diff (sheet counts, row labels, section boundaries) + value diff (parameter deltas, metric changes) | app/ingestion/differ.py | Auto-diff works |
| W6–W7 | Streamlit dashboard: asset browser (filter by country/tech), metric explorer, quarter-over-quarter comparison | app/ui/dashboard.py, asset_browser.py | UI live |
| W7–W8 | Diff visualization: change heatmaps, drill-down to individual cells, anomaly flagging (changes > threshold) | app/ui/diff_viewer.py |  |
| W8 | Integration testing, structural map validation against both quarterly files, performance tuning | tests/ | Phase 1 complete |

### Phase 1 Deliverables

- Upload a quarterly .xlsb/.xlsm and have it fully ingested into PostgreSQL in under 5 minutes

- Browse all 78 real assets with their 590+ parameters, filterable by country and technology

- View 170 quarterly metrics for any asset across all time periods

- Compare two quarterly versions: see exactly what changed (parameters, curves, metrics)

- Structural validation: flag new sheets, row insertions, named range shifts

# Phase 2: Reporting Engine

|  | PHASE 2: Automated Report Generation | M3–M4 |
| --- | --- | --- |

Goal: Replace the 21 manually maintained GTC Excel sheets with on-demand report generation from the database. Eliminates the GTC team’s manual sheet maintenance work.

## Month 3: Report Templates & FX Engine

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W9–W10 | GTC report templates: match formatting of PnL projections, BS projections, CF Capital Strategy, Quarterly Reports (USD/EUR) | app/reports/gtc_generator.py, templates/ | Templates ready |
| W10–W11 | FX conversion engine: EUR-to-USD using FX rates from Time Inputs (A). AGP proportionate share calculation (ownership %) | app/reports/fx_engine.py | FX engine live |
| W11–W12 | Fiscal year mapping: FY26A+F, FY26B, FY27B, FY28F, FY29F. Map quarterly metrics to fiscal year buckets | app/reports/fiscal_mapper.py | Fiscal mapping |

## Month 4: Report Generation API & Comparison Reports

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W13 | Report generation API: generate all 21 GTC-equivalent sheets as .xlsx on demand via FastAPI endpoint | app/api/reports.py | API live |
| W14 | Comparison reports: side-by-side version comparison with delta highlighting. Multi-scenario comparison template | app/reports/comparison.py | Comparison reports |
| W14 | Streamlit report builder: select version, scenario, output format. Download generated Excel with audit metadata | app/ui/report_builder.py | Phase 2 complete |

### Phase 2 Deliverables

- Generate all 21 GTC reporting sheets (PnL, BS, CF, QRep, Valuation, Cash Breakeven) on demand

- Reports include audit trail: version_id, generation timestamp, source data hash

- FX conversion (EUR/GBP to USD) applied automatically

- Side-by-side comparison reports between any two quarterly versions

# Phase 3: Calculation Engine — Core

|  | PHASE 3: Python Financial Model (P&L Blocks) | M4–M7 |
| --- | --- | --- |

Goal: Rebuild the core P&L calculation blocks from Project Level Workings in Python. Each block is validated against Excel output for all 120 assets with a <0.01% divergence target.

This phase covers rows 136–927 of Project Level Workings: Flags, Production, Revenue (the most complex block at 348 rows), OpEx, Depreciation, VAT, and Working Capital.

## Month 5: Flags, Production & Revenue Foundation

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W15–W16 | Flags & Timings engine (PLW R136–R214): Solar/BESS on/off, inflation flags, construction/operation periods, FC dates | app/engine/flags.py | Flags validated |
| W17–W18 | Production engine (PLW R247–R272): Solar degradation, BESS capacity/degradation, availability, seasonality | app/engine/production.py | Production validated |
| W18–W19 | Revenue foundation: Generation waterfall (PLW R276–R310), PPA Contract 1 with CfD logic (PLW R312–R342) | app/engine/revenue.py | Revenue started |

## Month 6: Revenue Engine (Country-Specific Contracts)

The revenue engine is the most complex block — 348 rows covering 6 contract types across 3 countries. This month completes the full revenue waterfall.

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W19–W20 | PPA Contract 2: Floor PPA, SDE subsidy, Fixed Price PPA with EEG switch. SDE++ scheme (PLW R388–R423) | app/engine/revenue.py |  |
| W20–W21 | EEG contracts (PLW R425–R447), GoO/REGO certificates: contracted GoO 1&2 + merchant GoO (PLW R472–R499) | app/engine/revenue.py |  |
| W21–W22 | BESS Revenue: Tolling, Floor, Capacity Market, CIDT, Merchant (PLW R515–R591). Revenue totals & 10-year realized prices | app/engine/revenue_bess.py | Revenue validated |

## Month 7: OpEx, Depreciation, VAT & Working Capital

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W22–W23 | OpEx engine (PLW R624–R713): Solar O&M (period 1/2), land lease (fixed + revenue-dependent), insurance, BESS OpEx | app/engine/opex.py | OpEx validated |
| W23–W24 | Depreciation engine (PLW R715–R810): 6 Solar asset categories + BESS, tax depreciation, accelerated depreciation | app/engine/depreciation.py | D&A validated |
| W24–W25 | VAT engine (PLW R812–R882): VAT on CapEx/Revenue/OpEx, VAT facility, refund cycle. Working Capital (PLW R884–R927) | app/engine/vat.py, working_cap.py |  |
| W25–W26 | Integration: assemble Income Statement (Revenue − OpEx = EBITDA − D&A = EBIT). Validate full P&L against Excel for all 120 assets | app/engine/statements.py | Phase 3 complete |

### Phase 3 Deliverables

- Python calculation engine covering Flags → Production → Revenue → OpEx → D&A → VAT → Working Capital

- Each block validated against Excel output for all 120 asset slots

- Divergence target: <0.01% for all metrics across all assets

- Country-specific logic implemented: UK (CfD, 11kV), DE (EEG, SDE++), NL (SDE++)

- BESS revenue fully modeled: Tolling, Floor, Capacity Market, CIDT, Merchant

# Phase 4: Calculation Engine — Financing & Valuation

|  | PHASE 4: Debt, Tax, Distribution & IRR | M7–M9 |
| --- | --- | --- |

Goal: Complete the calculation engine with the financing stack: Senior Debt (including DSCR sculpting with iterative solver), Tax, Funding, Distribution Waterfall, and Valuation (IRR via XIRR).

## Month 8: Senior Debt & Tax

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W27–W28 | Senior Debt engine (PLW R929–1033): DSCR sculpting with iterative solver (Newton-Raphson), drawdown, scheduled repayment, cash sweep, interest hedging | app/engine/debt.py | Debt validated |
| W28–W29 | Reserve Security (PLW R1035–1084): DSRA/DSRF sizing, MRA, Repowering CapEx account | app/engine/reserves.py | Reserves validated |
| W29–W30 | Tax engine (PLW R1095–1157): Corporation Tax (tiered rates DE/UK/NL), Local Tax (DE add-backs), tax loss carry-forward, tax depreciation adjustments | app/engine/tax.py | Tax validated |

## Month 9: Funding, Distribution & Valuation

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W30–W31 | Funding Calcs (PLW R1160–1234): Sources & Uses, SHL (drawdown, IDC, principal, interest), commitment fees | app/engine/funding.py | Funding validated |
| W31–W32 | Distribution Waterfall (PLW R1258–1385): Covenants (DSCR/LLCR), SHL repayment, dividends, cash sweep, equity buy-back | app/engine/distribution.py | Waterfall validated |
| W33–W34 | Valuation (PLW R1388–1418): Project IRR (FCFF → XIRR), Equity IRR (Distributions), Equity IRR (CF for Equity). Full Financial Statements assembly | app/engine/valuation.py | Phase 4 complete |

### Phase 4 Deliverables

- Complete Python financial model: all 1,609 rows of Project Level Workings replicated

- DSCR sculpting with iterative solver handles the circular reference (Debt ↔ DSCR)

- Full Financial Statements: Income Statement, Cash Flow, Balance Sheet assembled from calculation blocks

- IRR calculation via XIRR matches Excel within 1 basis point

- Quarterly consolidation block generates output matching the Quarterly Output sheet

# Phase 5: Scenario Engine

|  | PHASE 5: Real-Time Sensitivity Analysis | M9–M10 |
| --- | --- | --- |

Goal: Build the scenario/sensitivity engine that makes the entire project worthwhile — drop analysis time from 2–3 hours to under 5 seconds by implementing selective recalculation via a dependency graph.

## Month 10: Dependency Graph & Selective Recalculation

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W35–W36 | Dependency graph: map which calculation blocks depend on which inputs. Mirror the 24 Sensis lever slots | app/engine/dependency_graph.py | Graph built |
| W36–W37 | Scenario override system: parameter overrides stored as deltas from baseline. Asset-level and portfolio-level targeting | app/api/scenarios.py, models/scenario.py | Overrides work |
| W37–W38 | Selective recalculation: only recalculate affected assets and affected blocks. Example: changing Net Production for 3 DE assets recalculates only those 3 | app/engine/selective_calc.py | Selective recalc |
| W39–W40 | Parallel execution: run N scenarios concurrently (multiprocessing). Sensitivity table generation. Scenario comparison UI in Streamlit | app/ui/scenario_builder.py | Phase 5 complete |

### Phase 5 Deliverables

- Change any of the 24 Sensis levers for any subset of assets and get results in < 5 seconds

- 24-scenario sensitivity run across 3 assets completes in < 30 seconds

- Full portfolio recalculation (all 120 assets) completes in < 2 minutes

- Scenario comparison: side-by-side results with delta highlighting

- Sensitivity tables: matrix view of IRR/NPV/DSCR across parameter ranges

# Phase 6: Satellite Frontends & Polish

|  | PHASE 6: Multi-Team Platform | M11–M12 |
| --- | --- | --- |

Goal: Extend the platform with dedicated frontends for BD, Investment, and Debt teams. Each team gets their own ingestion, analysis dashboard, and reporting tailored to their workflow.

## Month 11: BD & Investment Team Frontends

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W41–W42 | BD team frontend: pipeline valuation dashboard, deal screening (filter by IRR/capacity/country), development stage tracking | app/ui/bd_dashboard.py | BD frontend live |
| W43–W44 | Investment team frontend: portfolio analytics, IRR attribution (by country, technology, vintage), waterfall charts, concentration analysis | app/ui/investment_dashboard.py | Investment frontend |

## Month 12: Debt Team, Integration & Launch

| Week | Deliverable | Key Files / Components | Milestone |
| --- | --- | --- | --- |
| W45–W46 | Debt team frontend: covenant monitoring (DSCR/LLCR thresholds), refinancing scenario builder, debt maturity profile | app/ui/debt_dashboard.py | Debt frontend live |
| W47 | Integration testing: end-to-end validation across all modules. Performance optimization (database query tuning, caching) | tests/integration/ | Full test pass |
| W48 | Documentation, user training materials, deployment to production environment. Handover and launch | docs/ | Production launch |

### Phase 6 Deliverables

- BD team: pipeline valuation dashboard with deal screening and development tracking

- Investment team: portfolio analytics with IRR attribution and concentration analysis

- Debt team: covenant monitoring with DSCR/LLCR alerts and refinancing scenarios

- Full platform deployed to production with documentation and training

# Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Revenue engine complexity (348 rows, 3 countries, 6 contract types) | High | High | Build incrementally with per-block validation. Revenue is allocated 6 weeks (the longest single block). |
| DSCR circular reference divergence | Medium | High | Iterative solver with configurable tolerance. Cross-validate against Excel for every asset. |
| Quarterly Excel structural changes beyond row offsets | Medium | Medium | Structural Map fingerprint detects any drift. Human-in-the-loop approval for structural changes. |
| VBA macro logic not fully captured | Medium | Medium | Reverse-engineer macro behavior from input/output comparison. Keep Excel as validation oracle. |
| Performance at portfolio scale (120 assets x 420 months) | Low | Medium | NumPy vectorisation. Selective recalculation via dependency graph. Profile and optimize in Phase 5. |
| New asset types or contract schemes added by ASE | Low | Low | Modular engine design allows adding new revenue/contract modules without rewriting existing code. |

# Team & Resource Requirements

| Role | Phases | Responsibilities |
| --- | --- | --- |
| Backend Engineer (Senior) | 1–6 | FastAPI, PostgreSQL schema, ingestion pipeline, API design |
| Financial Engineer | 3–5 | Translate Excel formulas to Python. Deep PF domain knowledge required. |
| Frontend / Streamlit Dev | 1–6 | Dashboard, scenario builder, report UI, satellite team frontends |
| Data Engineer | 1–2 | Database optimization, migration scripts, data validation framework |
| QA / Validation | 3–6 | Cross-validate Python engine vs Excel. Regression testing. |
| Product Manager (GM) | 1–6 | Requirements, prioritization, stakeholder alignment with ASE/BD/Investment/Debt |

# Success Criteria

| # | Criterion | Target | Phase |
| --- | --- | --- | --- |
| 1 | Excel ingestion time (full quarterly file) | < 5 minutes | Phase 1 |
| 2 | Quarterly diff generation | < 30 seconds | Phase 1 |
| 3 | Report generation (all 21 GTC sheets) | < 2 minutes | Phase 2 |
| 4 | Calculation engine vs Excel divergence | < 0.01% all metrics | Phase 3–4 |
| 5 | Single-asset scenario recalculation | < 1 second | Phase 5 |
| 6 | 3-asset targeted sensitivity run | < 5 seconds | Phase 5 |
| 7 | 24-scenario sensitivity matrix | < 30 seconds | Phase 5 |
| 8 | Full portfolio recalculation (120 assets) | < 2 minutes | Phase 5 |
| 9 | Quarterly update cycle (ingest + diff + approve) | < 1 hour total | Phase 1–2 |
| 10 | Platform uptime | 99.5% | Phase 6 |

End of Document